## Cover Page
Document Version # | Author | Date | Action
1 | mai ali | 2021-10-19 | Created
Copyright © 2017 ITWorx Education
Template Version 1.0
[Type Project Name]
Configuration Management Plan
Document Change Control

## 1-Working Environment
Working Environment
The PL /TL defines the (SW specification, HW specification, servers URLs, etc.) of the project working environments in the below sections to be accessible by all project's team members and to be communicated to CMO to create the needed working environment.
1. Development Environment
2. Integration Environment
3. Testing Environment
4. Deployment Environment

## 2-Folders Structure
Folders Structure
Main Folder | Folder | Sub Folder
Source Code | Folder | Any
| Folder | Executable files
Documents | Change Requests | CR 1
| Design | Design Meetings
Design Review
Documents
Emails
GUI
| Development | Builds
Code Review
Mails
Unit Testing
| Project Management | Closure
Estimation
Measurements (for Profitability / EVM)
Planning
Tracking
Leasson Learned
Client Communication (client feedback, imp. mails, etc)
Proposal
Quality Assurance
| Release Management | Release Documents (Release Notes, Deployment guide, package tracker, etc)
| Requirements | Bidirectional Tracebility Matrix
Mails
Requirements Reviews
Requirements Gathering
Sign Off
| Testing | Any
Note on C32: Bi-directional traceability matrix is added under this folder

## 3-Documents Versioning
Document Versioning & Naming Convention
Project Name on CM tool: | MOE_UAE_Teams_Integration
Column1 | Internal Documents | External Documents (Deliverables)
Documents Versioning Rule: | Version number starts with 0.1 and increment to 1.1, 1.2, ..., 1.9, 2.0, 2.1, etc. with no conditions. | Version number starts with 0.1 and increment to 1.1, 1.2, ..., 1.9, 2.0, 2.1, etc. with no conditions.
Documents Naming Convention: | Teams_DocumentName V | UAE MOE_MS_Teams_Integration_DocumentName V

## 4- CIs Baseline Plan
Configuration Items Baseline Plan
Reason/ Trigger | Label/ Tag Name | Content (Configuration Items) | Owner | Verifier | Requirements Sent to Client "Mandatory"
Requirements Sent to Client "Mandatory" | MOE UAE Teams Intergation _Requirements Document_Date_V + version number | Requirements Document | Sally Emad Eldien MN | Mai Ali /New PM | Design
Design | MOE UAE Teams Integration _design Document_Date_V + version number | Design Document | Yassin El wakeel | Mohamed el Saqqa | Internal Builds "Mandatory"
Internal Builds "Mandatory" | Teams_ + build # starting with 0.1 | Releasing Documents Source Code | Yassin El wakeel | Gehane Kamal | Client Demo Builds
UAT Builds | Teams_ + build # starting with 0.2 | Releasing Documents Source Code | Yassin El wakeel | Gehane Kamal | UAT Builds
External Release "Mandatory" | MOE UAE Teams Integration _number | Releasing Documents Source Code | Yassin El wakeel | CMO | External Release "Mandatory"
Note on D4: Configuration Items listed here should be reviewed before baseline(label/Tag).